## Slide 1
Investment Case Generator MVP Roadmap
10-week client plan | concept-first, source-grounded delivery
MVP demo: Oct 30, 2026
Milestone
Jul 27
Aug 10
Aug 24
Sep 7
Sep 21
Oct 5
Oct 19
01
Product Alignment
Jul 27-Aug 7
Product Alignment
02
Document Intake + Discovery
Aug 10-Aug 21
Intake + Discovery
03
Evidence Model
Aug 24-Sep 4
Evidence Model
04
Narrative Generation
Sep 7-Sep 18
Narrative Generation
05
Review + Export
Sep 21-Oct 2
Review + Export
06
Guardrails + Validation
Oct 5-Oct 16
Guardrails + Validation
07
Pilot Demo
Oct 19-Oct 30
Pilot Demo
Discovery & Alignment
MVP Build
Validation & Pilot
Nov 2-Nov 20: pilot refinement
Client decision points
Document types in scope | review and approval owner | priority output format | evidence threshold for client-ready drafts | unresolved funding recipient or investment vehicle fields
Roadmap assumes kickoff on July 27, 2026. Generated investment cases remain draft materials requiring human review; unsupported impact, cost, partner, timeline, and funding claims stay unresolved.